## Roll Out Plan
SharePoint 2016 Upgrade Farm Installation/Configuration
Implementer | Activity No. | Activity Description | Start Time | Finish Time | Duration (hh:mm) | Status Completed = C Incomplete = I | Pred | Comments | Range
John (Admin)1 | 1 | Install SharePoint Binaries | TO BE FILLED LATER | TO BE FILLED LATER | 6 | TO BE FILLED LATER | n/a
John (Admin) | 2 | Install critical SharePoint updates. | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a | Following updates will be installed all App and WFE servers: 1. KB3115299 2. KB3141486 3. KB3191880
John (Admin) | 3 | Configure Basic Service applications | TO BE FILLED LATER | TO BE FILLED LATER | 3 | TO BE FILLED LATER | n/a
John (Admin) | 4 | Create new Web Application with host header "intranet.contoso.com" on target SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
John (Admin) | 5 | Synchronize AD users with target SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a
John (Admin) | 6 | Configure workflow manager/client in target SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 3 | TO BE FILLED LATER | n/a | A simple SP Designer workflow will have to be created to validate workflow configuration.
John (Admin) | 7 | Configure outgoing emial | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a | Add spwebdev user to a gorup and ensue email is received
Colin (Developer) | 8 | Install missing service applications in target SP 2016 Farm. - In case of any | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a | All service applications that exit in old production environment should also be created in Target SP 2016 Farm.
Colin (Developer) | 9 | Extract farm solutions from old production Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 1
Colin (Developer) | 10 | Install farm solutions to target SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 2
| 11 | Truncate source Web Appliction content database log file. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 3
Colin (Developer) | 12 | Make read-only and then take backup of source Web Application content database from old production farm's SQL Instance. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 4
Day 1 - Rollout weekend
Implementer | Activity No. | Activity Description | Start Time | Finish Time | Duration (hh:mm) | Status Completed = C Incomplete = I | Pred | Comments | Range
John (Admin) | 13 | Remove old data | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a
John (Admin) | 14 | Backup content databases | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER |  | All user should have stopped using the portal by the time this backup happens
John (Admin) | 15 | Empty recycle bin | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER
John (Admin) | 16 | Set site as read only | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER
John (Admin) | 17 | Backup content databases (Emptied recycle bin) | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a
Colin (Developer) | 18 | Restore backup in SQL instance of target SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a
Colin (Developer) | 19 | Run Test-SP content DB script and fix show stopper issues reported by the script. | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 5 If this scripts returns show stopper errors than fixing those will require more time. Thats why buffer time is added
Colin (Developer) | 20 | Mount content database to target Web Application of SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 6
Colin (Developer) | 21 | Upgrade content database of target Web Application of SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 7
Colin (Developer) | 22 | Update content sources in search & execute full crawl. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a
Colin (Developer) | 23 | Portal Redesign Solutions Deployment | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a
Colin (Developer) | 24 | Features Activation | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
Colin (Developer) | 25 | Add Columns to the list (Home Site + 5 Departments) | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a
Colin (Developer) | 26 | Enable Item Scheduling on pages library (Home Site + 5 Departments) | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a
Colin (Developer) | 27 | BCS lists creation | TO BE FILLED LATER | TO BE FILLED LATER | 3 | TO BE FILLED LATER | n/a
Colin (Developer) | 28 | Create new content e.g; news, events and apps | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | New items need to created so that SharePoint can create crawled properties for newly added columns
Colin (Developer) | 29 | Full search crawl background task execution time. | TO BE FILLED LATER | TO BE FILLED LATER | 8 | TO BE FILLED LATER | n/a | Full crawl of 150+ GB site collection can take a full day
Colin (Developer) | 30 | Create Corporate landing Page | TO BE FILLED LATER | TO BE FILLED LATER | 1.5 | TO BE FILLED LATER | n/a
Colin (Developer) | 31 | Run Script to Set Publishing End Date of News Pages | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 14
Colin (Developer) | 32 | Create Managed Properties | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a
Colin (Developer) | 33 | Add Divs to News Page Layout | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
Colin (Developer) | 34 | User Targeted Alerts DB Creation + SSIS Package Deployment | TO BE FILLED LATER | TO BE FILLED LATER | 5 | TO BE FILLED LATER | n/a
Colin (Developer) | 35 | Configure My Site Host in the target SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a
Colin (Developer) | 36 | Remove Contoso web part references from all pages. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 8
Colin (Developer) | 37 | Remove Contoso farm solutions. | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a
Colin (Developer) | 38 | Remove Contoso Webpart reference from "/home" default.aspx page. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 9
Colin (Developer) | 39 | Add missing entries in web.config of the target Web Application of SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 1 | TO BE FILLED LATER | n/a
Colin (Developer) | 40 | Add "About Me" link in welcome.ascx control in top ribbon gear icon dropdown. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
Colin (Developer) | 41 | Deploy Contoso Workflow solution files and dll in all App and WFE servers. | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a | Solution files and dll will be deployed manually in all App and WFE servers.
Colin (Developer) | 42 | Configure search box dropdown. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
Colin (Developer) | 43 | Remove "Personalize this Page" link from top ribbon gear icon dropdown. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
Colin (Developer) | 44 | Turn off FSC on "SPSERS#10 template. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 10
Colin (Developer) | 45 | Turn off OneDrive mordern experience | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 11
Colin (Developer) | 46 | Embed CSS using script editor webpart in "Departments", "Apps", and "Calendar" subsites under "EN/". | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 12
Colin (Developer) | 47 | Fix "NewForm", "EditForm", and "DispForm" of "Absences" list. | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a | Refer "Script" worksheet. Script ID: 13
30.5
Day 2 - Rollout weekend
Implementer | Activity No. | Activity Description | Start Time | Finish Time | Duration (hh:mm) | Status Completed = C Incomplete = I | Pred | Comments | Range
Colin (Developer) | 48 | Department Landing Page + Add existing contents on landing pages (5 departments) | TO BE FILLED LATER | TO BE FILLED LATER | 24 | TO BE FILLED LATER | n/a
John (Admin) | 49 | Status Check | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a | Conference Call 333-333-3333 PIN: 2222 ( Check email to be certain the start time has not changed)
John (Admin) | 50 | Change DNS entry, AAM entry and IIS binding for old production farm & change to intranet.contoso.com. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a | DNS entry must be completed by John (Admin) IIS and AAM must be completed by Colin (Developer)
John (Admin) | 51 | Point the url intranet.contoso.com to the target Web application of SP 2016 Farm. | TO BE FILLED LATER | TO BE FILLED LATER | 0.25 | TO BE FILLED LATER | n/a
John (Admin) | 52 | Configure Load Balancer for target SP 2016 Web Application with new URL | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a
John (Admin) | 53 | Go Live!! -Send Communication | TO BE FILLED LATER | TO BE FILLED LATER | 0.5 | TO BE FILLED LATER | n/a | Contact Help Desk to send Contoso Family email.
Colin (Developer) / John (Admin) | 54 | Review the sites | TO BE FILLED LATER | TO BE FILLED LATER | 2 | TO BE FILLED LATER | n/a | Jason/Rudy = Public Sites, Ricky/Leo=Private Sites
31

## Scripts
Script ID | Script Purpose | Script Type | Code
1 | Extract farm solutions | PowerShell | Set-ExecutionPolicy -Scope Process -ExecutionPolicy Bypass if ( (Get-PSSnapin -Name Microsoft.SharePoint.PowerShell -ErrorAction SilentlyContinue) -eq $null ) { Add-PSSnapin Microsoft.SharePoint.Powershell } $farm = Get-SPFarm $dirName = "<Path>" Write-Host Exporting solutions to $dirName foreach ($solution in $farm.Solutions) { $id = $Solution.SolutionID $title = $Solution.Name $filename = $Solution.SolutionFile.Name Write-Host "Exporting ‘$title’ to …\$filename" -nonewline try { $solution.SolutionFile.SaveAs("$dirName\$filename") Write-Host " – done" -foreground green } catch { Write-Host " – error : $_" -foreground red } }
2 | Install farm solutions | PowerShell | #Load SharePoint Snapin Add-PSSnapin Microsoft.SharePoint.PowerShell $SolutionsDirectory = Read-Host 'Please enter directory path for solutions ' $WebApp = Read-Host 'Please enter the WebApplication Url ' #Get solutions to be depolyed Write-Output "Getting solutions to be deployed" $Solutions = Get-ChildItem -LiteralPath $SolutionsDirectory -Include *.wsp #verifies if directory is empty or not if($Solutions -eq $null) { Write-Output "No wsp packages found in directory" Exit } function InstallSolution($SolutionName) { Try { Install-SPSolution -Identity $Solution -GACDeployment -WebApplication $WebApp -Confirm:$false -ErrorAction Stop # Install-SPSolution -Identity $Solution -GACDeployment -Confirm:$false } Catch { <# if($($_.Exception.Message) -like "*this solution contains no resources scoped for a Web application*") { Install-SPSolution -Identity $Solution -GACDeployment -Confirm:$false } elseif($($_.Exception.Message) -like "*specify the -FullTrustBinDeployment parameter to suppress this warning*") { Install-SPSolution -Identity $Solution -GACDeployment -WebApplication $WebApp -Confirm:$false } else { Write-Output "Exception Message: $($_.Exception.Message)" } #> Write-Output "Exception Message: $($_.Exception.Message)" } } function WaitForTimer($wsp) { $Solution = Get-SPSolution -Identity $wsp if ($Solution -ne $null) { $Counter = 1 Write-Output "Waiting to finish solution timer job" while( ($Solution.JobExists -eq $true ) -and ( $Counter -lt 60 ) ) { Write-Output "Please wait..." sleep 5 $Counter++ } Write-Output "Finished the solution timer job" } } #deployes each solution iteratively foreach($Solution in $Solutions) { $Path = $Solution.FullName $Solution = $Solution.Name Write-Host "Proceeding to deploy $Solution" $GetSolution = Get-SPSolution $Solution -ErrorAction SilentlyContinue if($GetSolution -eq $null) { Add-SPSolution -LiteralPath $Path -Confirm:$false InstallSolution($Solution) } elseif($GetSolution.Deployed -eq $true) { if($GetSolution.DeploymentState -eq "GlobalDeployed") { Try { Uninstall-SPSolution -Identity $Solution -Confirm:$false -ErrorAction Stop WaitForTimer($Solution) Remove-SPSolution -Identity $Solution -Confirm:$false Add-SPSolution -LiteralPath $Path -Confirm:$false InstallSolution($Solution) } Catch { Write-Output "Exception Message: $($_.Exception.Message)" } } else { Try { Uninstall-SPSolution -Identity $Solution -Confirm:$false -AllWebApplications -ErrorAction Stop WaitForTimer($Solution) Remove-SPSolution -Identity $Solution -Confirm:$false Add-SPSolution -LiteralPath $Path -Confirm:$false InstallSolution($Solution) } Catch { Write-Output "Exception Message: $($_.Exception.Message)" } } } else { Remove-SPSolution -Identity $Solution -Confirm:$false Try { #Add and deploy solution Add-SPSolution -LiteralPath $Path -Confirm:$false InstallSolution($Solution) } Catch { Write-Output "Exception Message: $($_.Exception.Message)" } } #gets current state of solution WaitForTimer($Solution) Write-Output "" Write-Output "Getting current state of $Solution :" Get-SPSolution $Solution ¦ Format-List DisplayName, SolutionId, Deployed, DeployedServers, DeploymentState, LastOperationEndTime, LastOperationDetails } #Unload SharePoint Snapin Remove-PSSnapin Microsoft.SharePoint.PowerShell Write-Host "" Write-Host "Script execution finished."
3 | Truncate DB Log file | MS SQL | use Contoso_Portal go alter database Contoso_Portal set recovery simple go dbcc shrinkfile('Contoso_Portal_log',100) go alter database Contoso_Portal set recovery FUll go
4 | Make DB Readonly | MS SQL | USE [master] ALTER DATABASE [Contoso_Portal] SET READ_ONLY WITH ROLLBACK IMMEDIATE
5 | Test database against a Web app | PowerShell | Test-SPContentDatabase -name "<DB-Name>" -webapplication <Web-App-URL> -ServerInstance "<SQL-Server-Instance>"
6 | Attach DB to Web app | PowerShell | Mount-SPContentDatabase -name "<DB-Name>" -webapplication <Web-App-URL>
7 |  | PowerShell | $WebAppURL= "<Web-App-URL>" #Get all content databases of the particular web application $ContentDBColl = (Get-SPWebApplication -Identity $WebAppURL).ContentDatabases foreach ($contentDB in $ContentDBColl) { #Updade each content database Upgrade-SPContentDatabase -id $contentDB.Id -Confirm:$false }
8 | Filter/Delete coras works webpart references | MS SQL | use Contoso_Portal select 'http://contoso:1111' + '/' + AllDocs.DirName + '/' as Site, AllDocs.LeafName as Page, AllWebParts.tp_ID, AllWebParts.tp_WebPartTypeID, AllWebParts.tp_WebPartIdProperty, AllWebParts.tp_Assembly, AllWebParts.tp_Class, AllWebParts.tp_ContentTypeId, AllWebParts.tp_DisplayName, AllWebParts.tp_IsIncluded, AllWebParts.tp_Type, AllWebParts.tp_Deleted, AllWebParts.tp_ZoneID, AllWebParts.tp_View, AllWebParts.tp_Level from AllDocs inner join AllWebParts on AllDocs.Id = AllWebParts.tp_PageUrlID where AllWebParts.tp_Assembly like '%contoso%' OR AllWebParts.tp_Class like '%contoso%' OR AllWebparts.tp_DisplayName like '%coras%' --use Contoso_Portal --Delete --from AllWebParts --from AllDocs inner join AllWebParts on AllDocs.Id = AllWebParts.tp_PageUrlID --where AllWebParts.tp_Assembly like '%contoso%' OR AllWebParts.tp_Class like '%contoso%' OR AllWebparts.tp_DisplayName like '%contoso%'
9 | Filter/Delete citrix webpart references | MS SQL | n/a
10 | Disable FSC for template SPSERS#10 | PowerShell | Disable-SPWebTemplateForSiteMaster –Template SPSPERS#10
11 | Turn off OneDrive mordern experience | PowerShell | $Farm = Get-SPFarm $Farm.OneDriveUserExperienceVersion = [Microsoft.SharePoint.Administration.OneDriveUserExperienceVersion]::Version1 $Farm.Update()
12 | Fix style of table of contents webpart | CSS | <style> .level-section { list-style:none; padding-left:0px } </style>
13 | Fix "Absenses" list forms | JavaScript | rows[rows.length-16].style.display = "none"; rows[rows.length-15].style.display = "none"; rows[rows.length-8].style.display = "none"; rows[rows.length-2].style.display = "none"; rows[rows.length-6].style.display = "none"; rows[rows.length-5].style.display = "none"; rows[rows.length-4].style.display = "none"; rows[rows.length-3].style.display = "none";
14 | Set Publishing End Date of News Pages | PowerShell | Add-PSSnapin Microsoft.SharePoint.PowerShell $w = Get-SPWeb <Web URL> $pl = $w.Lists["Pages"] $pages = $pl.Items foreach ($page in $pages){ $pageLayout = $page.Properties["PublishingPageLayout"] $pageLayoutName = $pageLayout.split(',')[1].trim() if($pageLayoutName -eq "<Page Layout Name>") { $page.File.Name $page.File.TimeCreated if(($page.File.TimeCreated).AddDays(14) -lt (Get-Date)) { $page.File.CheckOut() $page.Properties["PublishingExpirationDate"] = (Get-Date((Get-Date).AddMinutes(5)) -Format s).ToString() $page.Update() $page.File.CheckIn("") $page.File.Publish("") $page.File.Approve("") } } }

## Contact Info
Company | Name | Email | Mobile Phone
Contoso
| John (Admin) | john-admin@contoso.com | 111-111-1111
Vendor
| Colin (Developer) | colin-developer@vendor.com | 222-222-2222
| Conference Bridge |  | 333-333-3333 PIN: 2222